## Sheet1
Weeks | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Background Research and Proposal:
Background Research
Proposal | [13 empty] | 100% Complete
Working On
Game Development: | [13 empty] | Future Estimation
Camera Controls | [13 empty] | Current Week
Game Menus
Json/Dialogue Parsing
Interacting with Items |  | ⅓ Done
Puzzles |  | ⅑ Done
3D Rooms |  | ⅑ Done
Player Customisation
Custom Settings |  | ½ Done
Bug Fixing and Polishing | [9 empty] | Not Started
Dialogue Writing |  | ¼ Done
Final Presentation:
Report | [6 empty] | Not Started
Poster | [10 empty] | Not Started
Additional Features
Save Data | [6 empty] | Not Started